## Instructions
Note: any pale green fields have calculations in them
Do all steps on "GamePlan Tab"
Step | 1 | Fill in release & date on row 1
Step | 2 | Change people, phone numbers, emails as appropriate in lines 4-18…specifically column E for pre-population of fields; however all are important
Step | 3 | Fill in column "C" where field is white
Step | 4 | Get required information from etl rows 22-28, whatever day/time the CR was opened is the task start date/time
Step | 5 | Get required information from mainframe rows 29-30, whatever day/time the CR was opened is the task start date/time
Step | 6 | Get required information from web row 31 whatever day/time the CR was opened is the task start date/time
Step | 7 | Enter start date/time from Step 4 into task 75
Step | 8 | Enter start date/time from Step 5 into task 76
Step | 9 | Fill in column "F" where white
Step | 10 | Fill appropriate name in column 'H' & "I" where white
Step | 11 | If you like the pale green fields can be changed to not have a color
Please delete this tab after GamePlan is filled out

## GamePlan
Name Pronunciation Release R3.22 Game Plan for 22/9/2022
ALL Task Times are Central Time and apply to the release only, unless the line is a mock only line Note: Recovery Plan contained within CR's
[5 empty] | Contact Info 1 | Contact Info 2 |  | Involved with plan
|  |  | Release Lead |  |  |  |  | Yes
|  |  | Recovery Coordinator: |  |  |  |  | Yes
|  |  | Release Web Coordinator: |  |  |  |  | Yes
|  |  | Release BSC: |  |  |  |  | Yes
|  |  | SMAC Business Objects on Call: |  |  |  |  | Yes
|  |  | SMAC Validator on Call : | Business User |  | AP |  | Yes
|  |  | DBA for Capacity Planning: | EIW-ML-DOTNET-Support | look in work order for name | G= TEST-Name Pronunciation |  | Yes
|  |  | EDA Infrastructure | EDA Infrastructure | look in work order for name | EDA Infrastructure Email group |  | No
|  |  | ETL Floating Cell |  | 999-999-999 |  |  | Yes
|  |  | Web Deployment Team | .NET Team
Please email task completion notifications to G= TEST-Capacity
TaskNbr | Type | Release Applicable | Task Description | Duration | Task Start | Task End | Task Owner | Task Validator | Completion | Mock Done
Preperation
Technology Prep
10 | Prep | Yes | ETL PROD & BCP work CR#: CR00000001 - Starting at 4:00 PM CT on 2/7/2022 - Install | 0.5 | 2022-02-05 16:00 | 2022-02-05 16:15 |  | N/A | Type in Completion Date
10a | Prep | Yes | DBA (EIW-DBASupport - WO#: WO0000001 | 0 | 2022-02-05 16:00 | 2022-02-05 16:15 |  | N/A | Type in Completion Date | #REF!
25 | Prep | Yes | Web PROD & BCP Work CR00000001 4:00 PM CT on 2/16/2022 | 0.25 | 2022-02-05 16:00 | 2022-02-05 16:15 |  | N/A | Type in Completion Date
30 | Prep | Yes | Set up Game Plan Review internal to team | 0.25 | 2022-08-01 10:30 | 2022-08-01 10:45 |  | N/A | Type in Completion Date | N/A
35 | Prep | Yes | Internal MOCK/PROD/BCP Game Plan Review | 1 | 2022-08-05 10:30 | 2022-08-05 11:30 |  | N/A | Type in Completion Date
40 | Prep | Yes | Request DBA confirmation that mock database looks exactly like production before running mock | 1 | 3:00PM 8/9/2019 | 2022-08-09 16:00 |  | N/A | Type in Completion Date | N/A
45 | Prep | Yes | Confirm that MOCK database looks exactly like PROD, before running scripts. | 2 | 2022-08-09 16:00 | 2022-08-09 18:00 |  | 0 | Type in Completion Date | N/A
50 | Prep | Yes | Review Game Plan with Business Partners | 0.5 | 2022-02-05 15:00 | 2022-02-05 15:30 |  | N/A | Type in Completion Date
55 | Prep | Yes | Email to business partners to ensure they are aware of responsibilities surrounding install containing info below: | 0.25 | 2022-02-09 08:00 | 2022-02-09 08:15 |  | N/A | Type in Completion Date
55a | Prep | Yes | Table list : PROJECT_DATA TM_DATA STAMP_DATA TM_AU_DATA TM_FORECAST PROJECT_SKILLS TM_SKILLS INTAKE_DATA SDLC_DATA | 0 | 2022-02-09 08:00 | 2022-02-09 08:15 |  | N/A | Type in Completion Date | #REF!
55c | Prep | No | comfirmation of responsibilities surrounding day one files to updated files to current COB date | 0 | N/A | N/A |  | N/A | N/A | N/A
55d | Prep | Yes | provision of any special file/sql loads to technology two days prior to install | 0 | 2022-02-09 08:00 | 2022-02-09 08:15 |  | N/A | Type in Completion Date | 0
55e | Prep | Yes | ask if any data updates will be performed outside of table that need to be supported | 0 | 2022-02-09 08:00 | 2022-02-09 08:15 |  | N/A | Type in Completion Date | 0
55f | Prep | No | provision of any processing variable information needed for install | 0 | N/A | N/A |  | N/A | N/A | 0
55g | Prep | Yes | confirm implementation start time with business | 0 | 2022-02-09 08:00 | 2022-02-09 08:15 |  | N/A | Type in Completion Date | N/A
55h | Prep | Yes | inform that issues found in Production after implementation will need to have a Production ticket open and not an ALM ticket. | 0 | 2022-02-09 08:00 | 2022-02-09 08:15 |  | N/A | Type in Completion Date | N/A
70 | Prep | Yes | Create Snapshot(s) for final install | 4 | 2022-02-08 | 2022-02-08 04:00 |  | N/A | Type in Completion Date
75 | Prep | Yes | Lock snapshot for final install and attach to CR | 0.25 | 2022-02-09 | 2022-02-09 00:15 |  | N/A | Type in Completion Date
80 | Prep | No | Work request(s) created for Add Hoc request WR?? | 0.25 | 2022-02-14 08:00 | 2022-02-14 08:15 |  | N/A | N/A
80a | Prep | Yes | Jobs on hold for technology(Copydown): copydown need to be set to copy from primary to secondary need to admtbl entry for newly tables For compares are there new tables that need to be added…... | 0 | 2022-02-14 08:00 | 2022-02-14 08:15 |  | N/A | N/A | 0
80b | Prep | Yes | Jobs to be taken off hold for technology (type in list): | 0 | 2022-02-14 08:00 | 2022-02-14 08:15 |  | N/A | N/A | 0
80c | Prep | Yes | Jobs to be force started for technology (type in list): | 0 | 2022-02-14 08:00 | 2022-02-14 08:15 |  | N/A | N/A
80d | Prep | Yes | Jobs to be force started for business data updates (type in list): Per Business there will be data updates that will need to be completed. At this time we do not know if this will be done as part of release or on Monday after implementation. Business is to provide update. | 0 | 2022-02-14 08:00 | 2022-02-14 08:15 |  | N/A | N/A | 0
Business Prep
100 | Prep | Yes | Business information needed prior to mock-prod/bcp install start to support environment: | 0.25 | 2022-02-05 15:00 | 2022-02-05 15:15 | Business User | 0 | Type in Completion Date
100a | Prep | No | processing variables | 0 | N/A | N/A | N/A | N/A | N/A | 0
100b | Prep | Yes | day one files TBD | 0 | 2022-02-05 15:00 | 2022-02-05 15:15 | Business User | 0 | Type in Completion Date | 0
100c | Prep | Yes | any special file/sql loads to technology two days prior to install | 0 | 2022-02-05 15:00 | 2022-02-05 15:15 | Business User | 0 | Type in Completion Date | 0
110 | Prep | Yes | Make sure that all business reporting is completed prior to install | 0.25 | 2022-02-16 17:00 | 2022-02-16 17:15 | Business User | 0 | Type in Completion Date
120 | Prep | Yes | Notify when pricing automation is complete (needed when pricing automation changes are going in on a Friday install) | 0.25 | 2022-02-16 17:00 | 2022-02-16 17:15 | Business User | 0 | Type in Completion Date
IMPLEMENTATION
Database, Cloud and OSS Grants Deploy
200 | Rel Mock | Yes | Apply PROD database changes according to the Database Change Request document (This includes validating of triggers and indexes.) NOTE: Changes can only start after the batch and the backups are completed | 1 | MOCK - 2/9/2022 PROD - 5:00 PM 2/16/2022 | #VALUE! | EIW-ML-DOTNET-Support | N/A | Type in Completion Date | N/A
200a | Rel | Yes | Semantic View deployment | 0 |  | Fri 1:00 AM 8/9/21 | EIW-ML-DOTNET-Support | N/A | Type in Completion Date
200b | Rel Mock | Yes | All other database changes | 0 | MOCK - 2/9/2022 PROD - 5:00 PM 2/16/2022 | Fri 1:00 AM 8/9/21 | EIW-ML-DOTNET-Support | N/A | Type in Completion Date
210 | Rel Mock | Yes | Send notification email when DBA changes are complete for Production | 0.25 | MOCK - 2/9/2022 PROD - 5:00 PM 2/16/2022 | #VALUE! | EIW-ML-DOTNET-Support | N/A | Type in Completion Date | N/A
220 | Rel | Yes | Apply BCP database changes according to the Database Change Request document (This includes validating of triggers and indexes.) NOTE: Changes can only start after the batch and the backups are completed | 1 | BCP - 5:00 PM 2/16/2022 | #VALUE! | EIW-ML-DOTNET-Support | N/A | Type in Completion Date
230 | Rel | #REF! | Send notification email when DBA changes are complete for BCP | 0.25 | BCP - 6:00 PM 2/16/2022 | #VALUE! | #REF! | N/A | #REF!
240 | Rel Mock | Yes | Verify that the correct table structures are in place for PROD and BCP. | 1.5 | MOCK -2/9/2022 PROD - 6:00 PM 2/16/2022 | #VALUE! | John P | N/A | Type in Completion Date
250 | Rel Mock | Yes | Validate database security | 1 | MOCK - 2/9/2022 PROD - 5:00 PM 2/16/2022 | #VALUE! | 0 | N/A | Type in Completion Date
260 | Rel Mock | #REF! | Send notification email to G=ML-DOTNET when database structure validations are complete | 0.25 | MOCK - 2/9/2022 PROD - 5:00 PM 2/16/2022 | #VALUE! | John P | N/A | #REF!
270 | Rel | Yes | Provide email with database compares to business | 0.25 | PROD - 7:30 PM 2/16/2022 | #VALUE! | John P | N/A | Type in Completion Date
CODE Deploy
310 | Rel | Yes | Web Install | 1.5 | 2022-02-16 18:00 | 2022-02-16 19:30 | .NET Team | 0 | Type in Completion Date
320 | Rel Mock | Yes | Send E-mail to DBA's that we are ready for code migration to PROD/BCP. | 0.05 | MOCK - 2/9/2022 PROD - 5:00 PM 2/16/2022 | #VALUE! | 0 | N/A | Type in Completion Date | N/A
330 | Rel Mock | No | Send E-mail to infrastructure for the work order assigned to them to implement in PROD/BCP. | 0.05 | N/A | #VALUE! | N/A | N/A | N/A
390 | Rel Mock | No | Execute infrastructure workorder in PROD/BCP | 0.25 | N/A | #VALUE! | N/A | N/A | N/A
Validation Tasks
410 | Rel | Yes | Web Validation | 0.5 | 2022-02-16 19:30 | 2022-02-16 20:00 | 0 | N/A | Type in Completion Date
440 | Rel Mock | No | Validate the infrastructure work | 0.5 | N/A | #VALUE! | N/A | N/A | N/A
Database and OSS Special Instructions
500 | Rel Mock | Yes | Execute DB special Instructions in PROD/BCP after database structures and permissions validated | 1 | 2022-02-16 18:00 | 2022-02-16 19:00 |  | N/A | Type in Completion Date
500a | Mock | Yes | Include hyperlink to special instruction location for mock | 0 | 2022-02-16 18:00 | 2022-02-16 19:00 | 0 | N/A | Type in Completion Date
500b | Rel - Prod | Yes | Include hyperlink to special instruction location for prod | 0 | 2022-02-16 18:00 | 2022-02-16 19:00 | 0 | N/A | Type in Completion Date | 0
500c | Rel - BCP | Yes | Include hyperlink to special instruction locationfor bcp | 0 | 2022-02-16 18:00 | 2022-02-16 19:00 | 0 | N/A | Type in Completion Date | 0
500d | Rel - UAT | Yes | Include hyperlink to special instruction location for uat | 0 | 2022-02-16 18:00 | 2022-02-16 19:00 | 0 | N/A | Type in Completion Date | 0
500e | Rel - SIT | Yes | Include hyperlink to special instruction location for sit | 0 | 2022-02-16 18:00 | 2022-02-16 19:00 | 0 | N/A | Type in Completion Date | 0
520 | Rel Mock | Yes | special file/sql loads file loads (i.e. set-up of previous day information for calculations, etc.) | 1 | 2022-02-16 18:00 | 2022-02-16 19:00 | Enter Development Team Assignment | N/A | Type in Completion Date
530 | Rel Mock | Yes | Send notification to business that the tables loads can be done | 0.25 | 2022-02-16 18:00 | 2022-02-16 18:15 |  | N/A | Type in Completion Date
540 | Rel Mock | Yes | Business to load tables in Prod & notify on completion | 1 | 2022-02-16 18:00 | 2022-02-16 19:00 | Business User | N/A | Type in Completion Date
540a | Rel Mock | Yes | Table list : PROJECT_DATA TM_DATA STAMP_DATA TM_AU_DATA TM_FORECAST PROJECT_SKILLS TM_SKILLS INTAKE_DATA SDLC_DATA | 0 | 2022-02-16 18:00 | 2022-02-16 19:00 | Business User | N/A | Type in Completion Date | 0
570 | Rel Mock | Yes | Inform Business that data updates can be peformed | 0.25 | 2022-02-16 18:00 | 2022-02-16 18:15 |  | N/A | Type in Completion Date
571 | Rel Mock | Yes | Business to inform technology when data update files are complete and correct | 0.5 | 2022-02-16 19:00 | 2022-02-16 19:30 | Business User | #REF! | Type in Completion Date
573 | Rel Mock | Yes | Businss to validate special file/sql loads file loads are showing expected results | 1 | 2022-02-16 19:00 | 2022-02-16 20:00 | Business User | 0 | Type in Completion Date
FINAL INSTRUCTIONS
600 | Rel Mock | Yes | validate all tasks are complete (through emails recevied) and game plan updated and send email to G= TEST-CapacityPlanning that all tasks are complete | 0.25 | 2022-02-16 20:00 | 2022-02-16 20:15 |  | N/A | Type in Completion Date
610 | Rel | Yes | Notify the business the implementation is complete | 0.25 | 2022-02-16 20:15 | 2022-02-16 20:30 |  | N/A | Type in Completion Date
Post Install Instructions
700 | Post Mock Rel | Yes | Check any new incoming file are available on BCP from source system | 1 | Type in expected task start date time | #VALUE! | Enter Development Team Assignment | N/A | Type in Completion Date
Formulas:
Contact Info 2 = IF([Release Applicable]="Yes",[Contact Info 2, row below],N/A)
Contact Info 2 = [Contact Info 1]+[Business User]/24
Contact Info 1 = IF([Release Applicable]="Yes",F19,N/A)
Contact Info 1 = [Contact Info 2, row above]
Mock Done = [Mock Done, row above]
Involved with plan = IF([Release Applicable]="Yes",E7,"N/A")
Task Owner = IF([Release Applicable]="Yes",E7,"N/A")
Task Owner = IF([Release Applicable]="Yes",H37,"N/A")

## R4.09 Rlse Items (hidden)
ENTERPRISE CHANGES
Items in the Release